## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | Your team name as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a buyer I want to see a list of products so that I choose what to purchase. | Given that I am on the e-store site when I am not on the Products page then I must see a means to navigate to the Products page. | Pass | SR; 3/19/24
| Given that I am not on the Products page when I choose the Products page then I am taken to the Products page. | Pass | SR; 3/19/24
| Given that I am on the Products page when there are no products in the inventory I see a message indicating that that there are no products available. | Pass | SR; 3/19/24
| Given that I am on the products page when there are products in the inventory then I see each product and short description. | Fail | SR; 3/19/24 We will create a description during sprint 3
| Given that I am on the products page when there are products in the inventory then I see a means to add each product to my shopping cart. | Pass | SR; 3/19/24
As a user I want to use a search bar so that I can search for specific products that match my wants | Given I enter a substring when I search for a product then I should see all products whose name contains that substring | Pass | SR; 3/7/2024
| Given I enter a substring that is not in any of the products names when I search for a product then I expect to see no products listed | Pass | SR; 3/7/2024
As a customer I want to be able to register an account so that I can save my information in the e-store | Given I don't have an account when I attempt to register an account and my username is unique then I expect to have a unique account created with a valid username of my choice. | Pass | VR; 3/18/2024
| Given I enter a username that is already in use when I attempt to register an account then I expect to not be able to register a new account with that username. | Pass | VR; 3/18/2024
As a User I want to log in so that I can have information personal to me. | Given my username is not registered when I attempt to log in with that username then I should not be logged in and I should be told that my information is incorrect. | Pass | VR; 3/18/2024
| Given my username is already registered when I attempt to log in with that username then I should be fully logged into the website. | Pass | VR; 3/18/2024
As a User I want to log out when I’m signed in so that my session is securely terminated. | Given I am logged in when I hit the log-out button, then I will log out of my account and end up at the login/register page | Pass | VR; 3/18/2024
As a customer I want to be able to add items from the cart so that I can choose what I’m going to purchase | Given I am a customer that has logged in when I go to add a product to my shopping cart then the item should be added and a confirmation should be sent. | Pass | EB; 3/19/2024
| Given I am an admin that has logged in, when I try to add a product to a shopping cart then there is no button to do so | Pass | EB; 3/19/2024
As a user I want to remove products from my cart so that I can avoid purchasing products that I no longer want to buy. | Given I am a customer that has logged in when I go to remove a product to my shopping cart then the item should be removed and a confirmation should be sent. | Pass | EB; 3/19/2024
| Given I am an admin when I want to access a shopping cart then I won't be able to. | Pass | EB; 3/19/2024
As a customer I want to be able to see the items in my shopping cart so that I know what I am purchasing. | Given I am customer logged in when I go to access my shopping cart then I expect to see all of the items within my shopping cart. | Pass | EB; 3/19/2024
| Given I am an admin when I go to access a shopping cart then I expect to be denied access | Pass | EB; 3/19/2024
As an Admin I want to be able to delete an item from the inventory so that users will no longer be able to purchase the item | Given a user is logged in as an admin when that user views the inventory management component then they see an option to delete products. | Pass | EB; 3/19/24; RL; 3/18/24
| Given a user is logged in as an admin when that user enters a valid product id and attempts to remove it then the product is removed from our inventory | Fail | EB; 3/19/2024; Because we decided to move away from deleting with ID's
| Given a user is logged in as an admin when that user enters an invalid product id and attempts to remove it then the product is not remove from our inventory | Fail | EB; 3/19/2024; Because we decanded remove remove it away from deleting wthenh ID's
As an Admin I want to be able to add a product to the inventory so that users will be able to purchase the product | Given a user is logged in as an admin when that user enters a valid product and attempts to add it then the product is added to our inventory |  | SR; 3/18/24 EB; 3/19/24
| Given a user is logged in as an admin when that user views the inventory management component then they see an option to add products. |  | SR; 3/18/24 EB; 3/19/24
| Given a user is logged in as an admin when that user enters an invalid product and attempts to add it then the product is not added to our inventory |  | SR; 3/18/24 EB; 3/19/24
As an Admin I want to be able to update a product from the inventory so that the store displays the correct product | **Given** a user is logged in as an admin **when** that user views the inventory management component **then** they see an option to update products. | Pass | SR; 3/18/2024
| **Given** a user is logged in as an admin **when** that user enters a valid product id and valid product information and attempts to updates it **then** the product is updated in our inventory | Fail | SR; 3/18/2024; Because we decided to move away from updating with ID's
| **Given** a user is logged in as an admin **when** that user enters an invalid product id or invalid product information and attempts to update it **then** the product is not updated in our inventory | Fail | SR; 3/18/2024; Because we decided to move away from updating with ID's