## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | Your team name as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a buyer I want to see a list of products so that I choose what to purchase. | Given that I am on the e-store site when I am not on the Products page then I must see a means to navigate to the Products page.
Given that I am not on the Products page when I choose the Products page then I am taken to the Products page.
Given that I am on the Products page when there are no products in the inventory I see a message indicating that that there are no products available.
Given that I am on the products page when there are products in the inventory then I see each product and short description.
Given that I am on the products page when there are products in the inventory then I see a means to add each product to my shopping cart.
As a user I want to use a search bar so that I can search for specific products that match my wants | Given I enter a substring when I search for a product then I should see all products whose name contains that substring | Pass | SR; 3/7/2024
| Given I enter a substring that is not in any of the products names when I search for a product then I expect to see no products listed | Pass | SR; 3/7/2024
As a customer I want to be able to register an account so that I can save my information in the e-store | Given I don't have an account when I attempt to register an account and my username is unique then I expect to have a unique account created with a valid username of my choice. | Pass | VR; 3/18/2024
| Given I enter a username that is already in use when I attempt to register an account then I expect to not be able to register a new account with that username. | Pass | VR; 3/18/2024
As a User I want to log in so that I can have information personal to me. | Given my username is not registered when I attempt to log in with that username then I should not be logged in and I should be told that my information is incorrect. | Pass | VR; 3/18/2024
| Given my username is already registered when I attempt to log in with that username then I should be fully logged into the website. | Pass | VR; 3/18/2024
As a User I want to log out when I’m signed in so that my session is securely terminated. | Given I am logged in when I hit the log-out button, then I will log out of my account and end up at the login/register page | Pass | VR; 3/18/2024